## Risk Analysis Scope
| HSEQ Qualitative Risk Analysis (Level 2) |  | - Scoping and Planning Tool
Workshop Topic |  | Change of Fire Suppression System in Sub Stations
Date |  | 07.07.14
Work Area Description |  | Sub Stations at Hope Downs
Team Members |  | Terry Mellor, Rob Stewart, Tony Morris, Cameron Raudino, Ray Mergard (Amerex), Todd Butler ( Mercury Fire Safety)
Facilitator |  | Brett Pascoe
What Has "Triggered" the risk assessment: | Hawcroft Consulting recently completed a Critical Risk Audit (CRA) of the Hope Downs 1 Operations. Part of this was reviewing the high potential fire risk areas. The report identified that 10 of our substations have inadequate protection due to relying on detections only system. The remaining 4 substations have gaseous fire suppression systems installed (FM 200). Hawcroft have recommended that the 10 unprotected substations have fire suppression systems installed. The Firepro Aerosol Suppressant system has been recommended as the preferred product over the currently used FM200 Gaseous Suppression.
Objectives: | To assess the operational and functional risk of installing the Firepro Aerosol Suppressant system into Electrical Sub Station instead of the currently used FM200 Gaseous Fire Suppression System.
Scope & Boundaries: | Includes, Compatability with existing infrastructure, effectiveness of fire suppression, health and safety exposures, environmental exposures, security of supply, environmental exposures, cost benefit realisation
Stakeholders and Risk Assessment Team: Who will be in the risk assessment team? | Terry Mellor, Rob Stewart, Tony Morris, Ray Mergard (Amerex), Todd Butler ( Mercury Fire Safety)
Timing: | Monday 7th July, 12:30 - 16:30
Venue: | Sante et Securite, Central Park Lvl 7, Perth
Where will the risk assessment be conducted?
Input Information: | MSDS sheets for Firepro product and FM200 product. FirePro CEA (draft) Du Pont website (FAQs for FM200) FirePro Website Australian Department of Environment website. National Industrial Chemicals Notification and Assessment Scheme - Full Public report HFC-227ea dated 6 May,1994
Describe the key information likely to be required to complete the risk assessment e.g. incident reports, procedures etc.
Describe any key Regulations and procedures that need to be considered: eg. Legislation and Regulations, Standards, Management plans, Codes of Practice, Manufacturer Instructions etc | AS4487-20013 for Condensed Aerosol Fire Extinguishing Systems ASISO14520-1 for Gaseous fire-extinguishing systems
Does the team have an understanding of the Risk Management Process? What training or information may be required.
Note on D6: This will populate all of the other relevant headings on the risk assessment record
Note on D7: This will populate all of the other relevant headings on the risk assessment record
Note on D8: This will populate all of the other relevant headings on the risk assessment record
Note on D9: This will populate all of the other relevant headings on the risk assessment record
Note on A11: Hazards identified without controls from a level 1 assessment. High degree of uncertainty remains after level 1 assessment Management of Change for major changes. Major Project Concept Studies (including design, construction, commissioning or decommissioning as applicable) Stakeholder concerns. (e.g. complaints or adverse symptoms) Regulatory driven Incidents with Maximum Reasonable Outcome of Low, Moderate, High - post incident review of controls from incident investigation. This excludes incidents with a maximum reasonable outcome of High that are considered as requiring a Level 3 assessment because of the nature of their maximum reasonable consequence (Major or Catastrophic) Recommendation from audit or management review Periodic review requirements for risk register (e.g. at least annually for critical and high risks)
Note on A12: Risks are analysed qualitatively - thus providing an efficient and effective method of identifying and evaluating single risk issues and developing risk management response plans and procedures. The Qualitative technique applies a team based approach and uses a standardized set of consequence and likelihood descriptors, together with a standardized matrix to classify the risk.
Note on A14: Decide on best team members and responsibilities. The team members should be knowledgeable in the hazard's) / aspects under review. Invite members in advance & confirm attendance The team should be made up of a minimum of three participants plus a facilitator & scribe (Where possible). The Risk Owner needs to be consulted about workshop involvement or make up. The team MAY be made up of a combination of people from various functions and levels within the organisation: Maintenance personnel Operational personnel Line management Technical specialists HSE specialist HSE representative(s) Management Contractor representatives Regulatory inspectors / advisors Scribe (optional but recommended for larger groups) Risk specialist (optional but may be required for more complex assessments)
Note on A16: Typically allow for 2-3 hrs minimum for a session to allow for continuity of discussion. You may need multiple sessions. A Hazard Scoping session may assist in planning time requirements. Ensure breaks. Ensure notice of “workshop in progress”, to control interruptions To ensure best use of time - limit interruptions from phones, blackberry, people interruptions, etc. Plan sessions around availability of key personnel. e.g.. shift handover, team meetings, etc
Note on A17: Need for BIG screen to show Risk Analysis Record Sheet Select suitable venue (ensure booked). Information recording equipment (computer, white board, butchers paper / wall charts). For existing site, consider off site (less distractions). On site is best if inspection or observation is required. Space to stick up drawings and move around. Caffeine, sugar, water, healthy snacks. Ensure comfort air conditioner, fresh air, bathroom facilities, quiet location
Note on A20: Ensure everyone understands objective & scope of session. Have material on system / activity / process to be reviewed, including physical & or process boundaries. Understanding of core assumptions. Identify potential conflict issues - contracts, vendors, history etc. Other information sources may include; Incident reports, Hazard or HAZOP studies, Capital Plans, Existing Risk Registers, Pre task risk information….

## Work Area Risk Analysis Record
#REF!
To record Predicted Risk unhide columns AF-AH
| Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory |  | Optional | Optional | Optional | Optional | Optional | Optional | Optional | Mandatory | Mandatory | Optional | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Dependent | Dependent | Optional | Optional |  | Optional | Optional | Optional | Optional | Optional
| Business Defined | Rio Tinto Defined | Rio Tinto Defined | Rio Tinto Defined | Free Text | Rio Tinto Defined | Rio Tinto Defined | Rio Tinto Defined | Business Defined |  | Rio Tinto Defined | Rio Tinto Defined | Rio Tinto Defined | Free Text | Free Text | Rio Tinto Defined | Free Text | Rio Tinto Defined | Free Text | Free Text | Rio Tinto Defined | Rio Tinto Defined | Rio Tinto Defined | Rio Tinto Defined | Free Text | Defined | Rio Tinto Defined | Free Text | Free Text | Free Text |  | Rio Tinto Defined | Rio Tinto Defined | Rio Tinto Defined | Business Defined | Free Text
RISK HEADER |  |  |  |  | RISK SCENARIO | [5 empty] | INHERENT RISK - Optional Data Capture |  |  |  |  | CURRENT RISK - mandatory data capture | [13 empty] | IMPROVEMENT ACTIONS - proposed new controls | Justification for Improvement action
Risk ID | Work Area Description | Hazard Type | Hazard Description (Sub-Type) | Operational Status | Scenario Description | Consequence Category | Consequence Sub-Category | Reference Source | Scenario Owner Position | Next Review Date | Consequence | Likelihood | Risk Rating | Last Review Date | Risk Comments | Cause Description | Cause Comments | Control Type Description | Control Comments | Impact Description | Consequence | Likelihood | Risk Rating | Status | Last Review Date | Quantitative Assessment Complete | Quantitative Risk Class | Quantitative Assessment Numerical Score | Risk Comments | Action Description |  | Predicted Consequence | Predicted Likelihood | Predicted Risk Rating | Action Owner Position | Action Status / Comments | Hazard Validation | Consequence Sub Category Validation
Example 1 | Work Area 1 | Gravity | Fall from Height | Normal Operation | A fall during ship to shore transfer may result in personal injury. | Personnel safety | Sprains / strains | C4 Working At Heights | Role 1 | 2012-03-01 | 5-Catastrophic | A-Almost certain | #REF! | 2010-03-01 |  | Procedures-Not used/not followed | Non-adherence to procedures, particularly the safe work conditions is the primary cause from events such as these. | 3 Engineering Controls | Safety barriers installed along length of wharf. Permit to work required to be complete and signed off before working in the area. | Person gets seriously hurt from fall, variable heights, and surfaces. | 3-Serious | B-Likely | #REF! | 3 Released | 2011-03-01 | Yes | III High | 0.0125 | Person gets seriously hurt from fall, variable heights, and surfaces. Several incidents of this nature have occurred, particularly during rough weather or increased windage on wharf, as such the risk has been evaluated considering the minimum controls for all conditions. | Install additional barricading along western section of wharf |  | 3-Serious | D-Unlikely | #REF! | Role 1 |  | ZGRAVITY | RT_020_000140
P01 | Electrical Substations | Substances | Heptafluoropropane | Emergency Conditions | Person in substation at time of fire suppressant discharge during maintenance/installation/other works | Personnel safety | Cardiac arrest | B1 Particulates & Gas Vapour Exposure | [7 empty] | Procedures-Not used/not followed | Accidental discharge exposing personnel to FM200 ; Activation through dust/electrical, maintenance activities etc | 3 Engineering Controls | Dual protection to activate, alarmed (visuala nd audio), emergency services, emergency procedures, training, access restrictions (inductions), dual egress doors, licensed, trained, competent personnel working on the system, licenses, SWP's, OEM procedures | Where concentrations may be greater than 5% then cardiac effects can result | 3-Serious | D-Unlikely | #REF! | [5 empty] | Discharges are known to occur but although medical treatments are not known to have occurred there is an expectation that this could occur. | Install aerosol fire suppressant (eg FirePro) | FirePro does not present the risk of cardiac arrest as Heptafluoropropane is not part of the chemical make-up. | 1-Minor | E-Rare | #REF! |  |  | REAL_SUB | RT_020_000140
P02 |  | Substances | Heptafluoropropane | Emergency Conditions | Person in substation at time of fire suppressant (FM200) fire condition discharge | Personnel safety | Asphyxiation | B1 Particulates & Gas Vapour Exposure | [7 empty] | Equipment difficulty-Design | Personnel are unable to remove themselves from the discharge area during fire | 3 Engineering Controls | Dual protection to activate, alarmed (visual nd audio), emergency services, emergency procedures, training, access restrictions (inductions), dual egress doors, | FM200 at temperature, creates the by-product, Hydrogen Chloride gas and carbon monoxide. When inhaled, Hydrochloric acid results from the lungs moisture which has severe toxic effects that can result in death . | 4-Major | E-Rare | #REF! | [5 empty] | This is not known to have occurred but remains a potential fatality risk. | Install aerosol fire suppressant (eg FirePro) | FirePro does not contain Heptafluoropropane. Therefore Hydrogen Chloride will not result when exposed to heat. | 1-Minor | E-Rare | #REF! |  |  | REAL_SUB | RT_020_000140
P03 |  | Sound / Vibration | Noise (Impact) | Emergency Conditions | Person in substation at time of fire suppressant (FM200) discharge | Health impact | Nervous System and Sense Organs | B2 Hearing Conservation | [7 empty] | Equipment difficulty-Design | Discharge of gas under pressure generates noise at >68db. This combined the audible alarms can potential leave people in the area disorientated, | 3 Engineering Controls | Dual protection to activate, alarmed (visual and audio), emergency services, emergency procedures, training, access restrictions (inductions), dual egress doors, | Causing disorientation and confusion resulting in personal injury | 2-Medium | D-Unlikely | #REF! | [5 empty] | The MRC injury from disorientation is believed to be a medical treatment type injury from sprains, cuts and contusions. | Install aerosol fire suppressant (eg FirePro) | The low pressure discharge of FirePro means that there is minimal generated noise. | 1-Minor | E-Rare | #REF! |  |  | ZSND_VIB | RT_020_000150
P04 |  | Thermal/Fire/Explosion | Contact - Cold Gas | Planned Maintenance | Person in substation and in the line-of-fire at time of suppressant (FM200) discharge | Personnel safety | Burns | M3 Hazard ID & Risk Management | [7 empty] | Equipment difficulty-Design | Discharge of gas (FM200) with personnel in the line-of-fire. | 4 Administrative Controls | PPE(Gloves) , procedures, risk assessments, SWP, competent, trained, licensed personnel, engineering | Frostbite burns | 3-Serious | E-Rare | #REF! | [5 empty] | As FM200 is a compressed gas, it is extremely cold when discharged. Exposure of bare skin to the gas being discharged can result in frostbite type injuries. As people will most likely remove themselves from the line of fire very quickly the exposure of a lost time type injury is seen as rare. | Install aerosol fire suppressant (eg FirePro). | FirePro is a non-refrigerant-based system, does not utilise compressed gas, no maintenance is required | 1-Minor | E-Rare | #REF! |  |  | ZTHERMAL | RT_020_000140
P05 |  | Pressure | Pneumatic | Planned Maintenance | FM200 Cylinder or component rupture/failure resulting in instantaneous gas release and cylinder fragmentation | Personnel safety | Crushing / internal injuries | M3 Hazard ID & Risk Management | [7 empty] | Equipment difficulty-Equipment / parts defective | Cylinder and/or component degradation or misuse / mishandling | 4 Administrative Controls | Inspection and testing regime, replacement program, OEM procedures, correct storage / secure; training, accreditation, licenses | Explosive risk resulting in penetrating injury, pressure waveform injuries, crush injuries | 4-Major | E-Rare | #REF! | [5 empty] | FM200 is supplied in high pressure vessels (bottles) that can deteriorate or be damaged over time. These bottles have been known to fail with explosive force resulting fatality within industry but it is unknown to have occurred with mining. | Install aerosol fire suppressant (eg FirePro). | FirePro is a low pressure discharge system that does not require large high pressure bottles. | 1-Minor | E-Rare | #REF! |  |  | ZPRESSURE | RT_020_000140
P06 |  | Natural environment/ecosystem | Ecosystem Change | Normal Operation | Gaseous discharge of FM200 produces global warming substances which are reportable to EPA. | Environmental impact | Contamination - Air | E4 Greenhouse Gas Emissions | [7 empty] | Procedures-Not used/not followed | FM200 chemical make-up has a global warming effect 2900 times greater than carbon dioxide. FM 200 has a 40 - 50 year lifespan of activity in the atmosphere. | 4 Administrative Controls | Inspection and testing regime, replacement program, OEM procedures, correct storage / secure; training, accreditation, licenses, legislated reporting requirements and possible fines, CMS | The global warming substances will be active for a period of 40 - 50 years. | 3-Serious | C-Possible | #REF! | [5 empty] | There is no opportunity to mitigate the damage from the gas being discharged therefore it is considered as having a long term environmental effect. As the volume of gas being release is limited it has been considered as having a MRC of Serious. Accidental discharges are known to occur. | Install aerosol fire suppressant (eg FirePro). | FirePro has zero global warming products and has a minimal life span of less than one day | 1-Minor | E-Rare | #REF! |  |  | ZENVIRON | RT_020_000160
P07 |  | Natural environment/ecosystem | Ecosystem Change | Normal Operation | Gaseous discharge of product produces global warming substances which are reportable to EPA | Compliance impact | Court order (potential) | M2 Legal & Other Requirements | [7 empty] | Procedures-Not used/not followed | Chemical make-up has global warming substances. Repeated discharges resulting in government/DOE investigation and possible fines | 4 Administrative Controls | Inspection and testing regime, replacement program, OEM procedures, correct storage / secure; training, accreditation, licenses, legislated reporting requirements and possible fines, CMS | Fine, compliance, increased contract management system requirements resulting from legislative body, community reputation | 3-Serious | C-Possible | #REF! | [5 empty] | As FM200 discharges are reportable to the EPA and accidental discharges are known to have occurred. It is concievable that moderate fines and conditions will result from multiple accidental discharges during the life of an operation. | Install aerosol fire suppressant (eg FirePro). | FirePro does not contain global warming chemicals and is not reportable to the EPA when discharged. | 1-Minor | E-Rare | #REF! |  |  | ZENVIRON | RT_020_000180
P08 |  | Thermal/Fire/Explosion | Fire - Surface - Fixed Plant | Normal Operation | Fire is not extinguished by FM200 due to non-integrity of the building or cabinet structure. | Production volumes | Quantity / output | M12 Disaster Management & Recovery | [7 empty] | Equipment difficulty-Design | FM200 is not contained effectively within the required area. | 4 Administrative Controls | Asset integrity testing, changes/modifications to assets, policy and procedures for access | Loss of substations for up to 12 months for rebuild, 3 months to enact a contingency | 4-Major | D-Unlikely | #REF! | [5 empty] | The substations at Hope Downs 1 are known to have problems maintaining holding the required levels of FM200 (5.8% v/v) for 20 minutes due to the pressurised release of the gas and area containment. | Install aerosol fire suppressant (eg FirePro) | As FirePro has a low pressure discharge rate of approx 2-6kpa the suppression chemical remains in the area longer and is less affected but area containment or area changes (modifications). | 2-Medium | D-Unlikely | #REF! |  |  | ZTHERMAL | RT_020_000120
P09 |  | Thermal/Fire/Explosion | Fire - Surface - Fixed Plant | Planned Maintenance | During re-fit of the sub-stations FM200 is non-operational, leaving an unprotected fire risk | Production volumes | Quantity / output | M3 Hazard ID & Risk Management | [7 empty] | Equipment difficulty-Design | During re-fits, FM200 is taken off-line to enable redesign. | 4 Administrative Controls | Manual fire notification process in enacted (Personnel on watch/standby). Fire extinguishers located adjacent to works area. | Loss of substations for up to 12 months for rebuild, 3 months to enact a contingency | 4-Major | E-Rare | #REF! | [5 empty] | Although manual fire watch activities are usually activated when fire suppression equipment is taken off line, this relies on people to ensure that the watch is maintained effectively. It is considered that this control is not 100% reliable and therefore the the potential for coplete loss of the sunstation is possible albeit rare. | Install aerosol fire suppressant (eg FirePro) | FirePro is not affected by internal changes to the structure of the building, no additional FirePro would be required. At worst case where an additional opening is created, additional FirePro units can be installed by accredited site electricians within a short time frame. | 2-Medium | E-Rare | #REF! |  |  | ZTHERMAL | RT_020_000120
P10 |  | Thermal/Fire/Explosion | Fire - Surface - Fixed Plant | Normal Operation | Loss of power to substation renders automated discharge of FM200 ineffective | Production volumes | Quantity / output | M3 Hazard ID & Risk Management | [7 empty] | Natural disaster / sabotage | Lightening strike, loss of mains power, loss of back-up power, critical failure of FIP | 3 Engineering Controls | Manual activation, back-up power, fire extinguishers, | Loss of substations for up to 12 months for rebuild, 3 months to enact a contingency | 4-Major | E-Rare | #REF! | [5 empty] | Lightening strike and power surge have the potential to start electrical fires in the substations whilst knocking out the FM200 activation circuitry in very rare circumstances | Install aerosol fire suppressant (e.g. FirePro) | FirePro automatically activates at 300 degrees Celsius and does not need to rely on electrical activation for discharge | 2-Medium | E-Rare | #REF! |  |  | ZTHERMAL | RT_020_000120
P11 |  | Thermal/Fire/Explosion | Fire - Surface - Fixed Plant | Normal Operation | Unable to source immediate supply of replacement cartridges for FirePro. This same risk exposure is in place for the FM200 system currently installed | Production volumes | Quantity / output | M3 Hazard ID & Risk Management | [7 empty] | Management system | No spares held on site or in Perth, sole provider in Australia unable to supply |  | Nil | Loss of substations for up to 12 months for rebuild, 3 months to enact a contingency | 4-Major | E-Rare | #REF! | [5 empty] | Unprotected substations until supply can be sourced (potentially 7 days). Manned fire watch would need to be in place increasing cost and also risk of fire due to human element being less effective than engineered control. | Perth-based warehouse to hold supplies. Site to hold a critical spares list. SLA to be developed with supplier. Addition of replacement parts to be added to BOM's. | Contingency for supply of componentry and consumables should be guaranteed. More than one supply avenue is desireable. | 2-Medium | D-Unlikely | #REF! |  |  | ZTHERMAL | RT_020_000120
P12 |  | Thermal/Fire/Explosion | Fire - Surface - Fixed Plant | Unplanned Maintenance | Delay to maintenance of FirePro due to lack of qualified personnel | Operating cost | Miscellaneous Expenses | M3 Hazard ID & Risk Management | [7 empty] | Training-Understanding needs improvement | Qualified personnel not available due to flights, accommodation, climatic events, availability (prior commitments) |  | Nil | Unprotected / reduced protection to substations until personnel can be sourced resulting in | 4-Major | E-Rare | #REF! | [5 empty] | Unprotected substations until qualified people can be mobilised. Manned fire watch would need to be in place increasing cost and also risk of fire due to human element being less effective than engineered control. | Training to accredit site-based electricians to install/maintain FirePro product | Maintaining site based capacity to maintain fire suppression systems will ensure that the integraty of the system is maintainable during unforseen issues getting Perth Based maintainers to site | 2-Medium | D-Unlikely | #REF! |  |  | ZTHERMAL | RT_020_000110
P13 |  | Social / Cultural | Economic / Community & Social Governance Capital | Commissioning & Ramp Up | Fire suppression systems do not meet current Australian and International standards | Compliance impact | Contract / service agreement | M3 Hazard ID & Risk Management | [7 empty] | Equipment difficulty-Design | Insurance company does not accept site fire suppression system as being adequate |  | Both FM200 and FirePro meet and certified to required Australian and International standards. AS4487 (2013) & UL 2775, and separately active fire listed. ACTI V Fire (CSIRO listed). FirePro is also certified against a 15 year lifespan. | Increased insurance costs. Reduced coverage. Negative shareholder perception/publicity | 1-Minor | E-Rare | #REF! | [5 empty] | Both Fm200 and FirePro are certified against Aus and Internal standards and if correctly installed will be accepted by the Insurance companies | Ensure that FirePro instalation is in compliance with appropriate Aus Standards |  | 1-Minor | E-Rare | #REF! |  |  | ZSOCCULT | RT_020_000180
P14 |  | Substances | Potassium | Normal Operation | Discharge of fire suppression system reduces visibility | Personnel safety | Abrasions | M3 Hazard ID & Risk Management | [7 empty] | Equipment difficulty-Design | Discharge of fire suppression system reduces visibility |  | FM200 is clear therefore there is no reduction in visibility. | Minimal impact | 1-Minor | E-Rare | #REF! | [5 empty] | No risk with FM200 regarding visibility. | FirePro has a white particulate causing a "white-out" reducing or eliminating visibility. Additional safety equipment (pre-evacuation warnings - visual and audio; system over-ride and delays; dual risk detection system as per AS4487 2013) provided in the installation will minimise potential exposure |  | 2-Medium | D-Unlikely | #REF! |  |  | REAL_SUB | RT_020_000140
P15 | [36 empty] | ZBIOLOG | RT_020_000090
P16 | [36 empty] | ZBIOLOG | RT_020_000090
P17 | [36 empty] | ZBIOLOG | RT_020_000090
P18 | [36 empty] | ZBIOLOG | RT_020_000090
P19 | [36 empty] | ZBIOLOG | RT_020_000090
P20 | [36 empty] | ZBIOLOG | RT_020_000090
P21 | [36 empty] | ZBIOLOG | RT_020_000090
P22 | [36 empty] | ZBIOLOG | RT_020_000090
P23 | [36 empty] | ZBIOLOG | RT_020_000090
P24 | [36 empty] | ZBIOLOG | RT_020_000090
P25 | [36 empty] | ZBIOLOG | RT_020_000090
P26 | [36 empty] | ZBIOLOG | RT_020_000090
P27 | [36 empty] | ZBIOLOG | RT_020_000090
P28 | [36 empty] | ZBIOLOG | RT_020_000090
P29 | [36 empty] | ZBIOLOG | RT_020_000090
P30 | [36 empty] | ZBIOLOG | RT_020_000090
P31 | [36 empty] | ZBIOLOG | RT_020_000090
P32 | [36 empty] | ZBIOLOG | RT_020_000090
P33 | [36 empty] | ZBIOLOG | RT_020_000090
P34 | [36 empty] | ZBIOLOG | RT_020_000090
P35 | [36 empty] | ZBIOLOG | RT_020_000090
P36 | [36 empty] | ZBIOLOG | RT_020_000090
P37 | [36 empty] | ZBIOLOG | RT_020_000090
P38 | [36 empty] | ZBIOLOG | RT_020_000090
P39 | [36 empty] | ZBIOLOG | RT_020_000090
P40 | [36 empty] | ZBIOLOG | RT_020_000090
P41 | [36 empty] | ZBIOLOG | RT_020_000090
P42 | [36 empty] | ZBIOLOG | RT_020_000090
P43 | [36 empty] | ZBIOLOG | RT_020_000090
P44 | [36 empty] | ZBIOLOG | RT_020_000090
P45 | [36 empty] | ZBIOLOG | RT_020_000090
P46 | [36 empty] | ZBIOLOG | RT_020_000090
P47 | [36 empty] | ZBIOLOG | RT_020_000090
P48 | [36 empty] | ZBIOLOG | RT_020_000090
P49 | [36 empty] | ZBIOLOG | RT_020_000090
P50 | [36 empty] | ZBIOLOG | RT_020_000090
P51 | [36 empty] | ZBIOLOG | RT_020_000090
P52 | [36 empty] | ZBIOLOG | RT_020_000090
P53 | [36 empty] | ZBIOLOG | RT_020_000090
P54 | [36 empty] | ZBIOLOG | RT_020_000090
P55 | [36 empty] | ZBIOLOG | RT_020_000090
P56 | [36 empty] | ZBIOLOG | RT_020_000090
P57 | [36 empty] | ZBIOLOG | RT_020_000090
P58 | [36 empty] | ZBIOLOG | RT_020_000090
P59 | [36 empty] | ZBIOLOG | RT_020_000090
P60 | [36 empty] | ZBIOLOG | RT_020_000090
P61 | [36 empty] | ZBIOLOG | RT_020_000090
P62 | [36 empty] | ZBIOLOG | RT_020_000090
P63 | [36 empty] | ZBIOLOG | RT_020_000090
P64 | [36 empty] | ZBIOLOG | RT_020_000090
P65 | [36 empty] | ZBIOLOG | RT_020_000090
P66 | [36 empty] | ZBIOLOG | RT_020_000090
P67 | [36 empty] | ZBIOLOG | RT_020_000090
P68 | [36 empty] | ZBIOLOG | RT_020_000090
P69 | [36 empty] | ZBIOLOG | RT_020_000090
P70 | [36 empty] | ZBIOLOG | RT_020_000090
P71 | [36 empty] | ZBIOLOG | RT_020_000090
P72 | [36 empty] | ZBIOLOG | RT_020_000090
P73 | [36 empty] | ZBIOLOG | RT_020_000090
P74 | [36 empty] | ZBIOLOG | RT_020_000090
P75 | [36 empty] | ZBIOLOG | RT_020_000090
P76 | [36 empty] | ZBIOLOG | RT_020_000090
P77 | [36 empty] | ZBIOLOG | RT_020_000090
P78 | [36 empty] | ZBIOLOG | RT_020_000090
P79 | [36 empty] | ZBIOLOG | RT_020_000090
P80 | [36 empty] | ZBIOLOG | RT_020_000090
P81 | [36 empty] | ZBIOLOG | RT_020_000090
P82 | [36 empty] | ZBIOLOG | RT_020_000090
P83 | [36 empty] | ZBIOLOG | RT_020_000090
P84 | [36 empty] | ZBIOLOG | RT_020_000090
P85 | [36 empty] | ZBIOLOG | RT_020_000090
P86 | [36 empty] | ZBIOLOG | RT_020_000090
Note on AB5: Mandatory if Quantitative Assessment Complete
Note on AC5: Mandatory if Quantitative Assessment Complete
Note on L7: Assessing inherent risk (without controls) is optional, not mandatory.
Note on B8: Drop Down List Add information to Business Defined Fields worksheet
Note on J8: Drop Down List Add information to Business Defined Fields worksheet
Note on Z8: All High and Critical risks must be updated annually. Low and Moderate risks must be updated every 3 years.
Note on AA8: All critical risks must undergo quantitative assessment. High risks with a consequence of major or catastrophic should be considered.
Note on AJ8: Drop Down List Add information to Business Defined Fields worksheet

## Hazard_Type (hidden)
Hazard Type Description | ABS Ref | Has Attributes Y/N
Biological | ZBIOLOG
Climatic / Natural Events | ZCLIMATIC
Electrical / Magnetic | ZELECTRIC
Ergonomics | ZERGONOMIC
External Threats | ZTHREAT
Gravity | ZGRAVITY
Lighting | ZLIGHT
Mechanical | ZMECHANIC
Natural environment/ecosystem | ZENVIRON
Personal / Behavioural | ZPERBEHA
Pressure | ZPRESSURE
Radiation | ZRADIAT | Y
Social / Cultural | ZSOCCULT
Sound / Vibration | ZSND_VIB
Substances | REAL_SUB | Y
Thermal/Fire/Explosion | ZTHERMAL
Vehicles/transportation | ZCOLLISION
Waste | ZWASTE
Work Environment | ZWORKENV

## Hazard (hidden)
Hazard Description | ABS Ref | Hazard Type Description | Hazard_Type ABS Code
Acetic Acid | 000000000589 | Substances | REAL_SUB
Acetone | 000000000268 | Substances | REAL_SUB
Acetylene | 000000000269 | Substances | REAL_SUB
Acid - Other | 000000000270 | Substances | REAL_SUB
Adhesives | 000000000590 | Substances | REAL_SUB
Alumina | 000000000613 | Substances | REAL_SUB
Alumina Fluorinated | 000000000271 | Substances | REAL_SUB
Alumina Hydrate | 000000000272 | Substances | REAL_SUB
Alumina Primary | 000000000273 | Substances | REAL_SUB
Alumina Secondary | 000000000588 | Substances | REAL_SUB
Aluminium | 000000000274 | Substances | REAL_SUB
Aluminium Fluoride | 000000000275 | Substances | REAL_SUB
Ammonia | 000000000614 | Substances | REAL_SUB
Ammonium Hydroxide | 000000000481 | Substances | REAL_SUB
Ammonium Nitrate | 000000000482 | Substances | REAL_SUB
Ammonium Sulfate | 000000000483 | Substances | REAL_SUB
ANFO (Ammonium Nitrate Fuel Oil Mix) | 000000000484 | Substances | REAL_SUB
Argon | 000000000277 | Substances | REAL_SUB
Arsenic | 000000000278 | Substances | REAL_SUB
Arsenic Trioxide | 000000000651 | Substances | REAL_SUB
Arsine Gas | 000000000652 | Substances | REAL_SUB
Asbestos | 000000000661 | Substances | REAL_SUB
Aviation Fuel | 000000000279 | Substances | REAL_SUB
Barium | 000000000280 | Substances | REAL_SUB
Bauxite | 000000000281 | Substances | REAL_SUB
Bauxite Residue | 000000000615 | Substances | REAL_SUB
Benzene | 000000000282 | Substances | REAL_SUB
Benzo(a)pyrene | 000000000283 | Substances | REAL_SUB
Benzyl Alcohol | 000000000284 | Substances | REAL_SUB
Beryllium | 000000000616 | Substances | REAL_SUB
Biocides | 000000000285 | Substances | REAL_SUB
Blasting Fumes | 000000000617 | Substances | REAL_SUB
Borates Dust | 000000000618 | Substances | REAL_SUB
Boron | 000000000619 | Substances | REAL_SUB
Brake Fluid | 000000000591 | Substances | REAL_SUB
Butane | 000000000287 | Substances | REAL_SUB
Cadmium | 000000000620 | Substances | REAL_SUB
Calcium Hydroxide (Hydrated Lime) | 000000000486 | Substances | REAL_SUB
Calcium Hypochlorite | 000000000592 | Substances | REAL_SUB
Calcium Oxide (Quick Lime) | 000000000487 | Substances | REAL_SUB
Carbon Dioxide | 000000000621 | Substances | REAL_SUB
Carbon Disulfide | 000000000622 | Substances | REAL_SUB
Carbon Monoxide | 000000000623 | Substances | REAL_SUB
Carcinogens | 000000000290 | Substances | REAL_SUB
Caustic Soda | 000000000291 | Substances | REAL_SUB
Ceramic Fibres | 000000000624 | Substances | REAL_SUB
Chemicals - Mixed | 000000000722 | Substances | REAL_SUB
Chlorine | 000000000292 | Substances | REAL_SUB
Chlorofluorocarbons | 000000000625 | Substances | REAL_SUB
Chromic Acid | 000000000293 | Substances | REAL_SUB
Chromium III | 000000000294 | Substances | REAL_SUB
Chromium VI | 000000000626 | Substances | REAL_SUB
Coal Tar Pitch Volatiles | 000000000627 | Substances | REAL_SUB
Coke | 000000000296 | Substances | REAL_SUB
Copper | 000000000297 | Substances | REAL_SUB
Copper Smelter Process Dust (ESP/WHB) | 000000000489 | Substances | REAL_SUB
Copper Sulfate Pentahydrate | 000000000490 | Substances | REAL_SUB
Cresylic Acid | 000000000491 | Substances | REAL_SUB
Cryogenic Liquids | 000000000299 | Substances | REAL_SUB
Cryolite (Bath) | 000000000301 | Substances | REAL_SUB
Cyclohexane | 000000000300 | Substances | REAL_SUB
Degreaser | 000000000303 | Substances | REAL_SUB
Detergents | 000000000304 | Substances | REAL_SUB
Diesel Exhaust Particulate (DP/DPM) | 000000000628 | Substances | REAL_SUB
Diesel Exhaust Vapours | 000000000572 | Substances | REAL_SUB
Diesel Fuel | 000000000305 | Substances | REAL_SUB
Dross | 000000000306 | Substances | REAL_SUB
Dust - Coal | 000000000653 | Substances | REAL_SUB
Dust - Fugitive emissions from operations | 000000000732 | Substances | REAL_SUB
Dust - Inhalable | 000000000629 | Substances | REAL_SUB
Dust - Organic | 000000000631 | Substances | REAL_SUB
Dust - Respirable | 000000000630 | Substances | REAL_SUB
Dust - Wood | 000000000632 | Substances | REAL_SUB
Entonox | 000000000659 | Substances | REAL_SUB
Ethane | 000000000307 | Substances | REAL_SUB
Ethanol | 000000000308 | Substances | REAL_SUB
Ethyl Acetate | 000000000309 | Substances | REAL_SUB
Ethyl Benzene | 000000000310 | Substances | REAL_SUB
Ethylene | 000000000311 | Substances | REAL_SUB
Ethylene Glycol (Coolant) | 000000000593 | Substances | REAL_SUB
Explosives - Others | 000000000312 | Substances | REAL_SUB
Ferric Sulfate | 000000000586 | Substances | REAL_SUB
Fertilizer | 000000000313 | Substances | REAL_SUB
Fire Suppressant | 000000000314 | Substances | REAL_SUB
Flocculant | 000000000318 | Substances | REAL_SUB
Flotation Reagents | 000000000319 | Substances | REAL_SUB
Fluoride | 000000000633 | Substances | REAL_SUB
Fluorine | 000000000321 | Substances | REAL_SUB
Flux | 000000000322 | Substances | REAL_SUB
Grease | 000000000323 | Substances | REAL_SUB
Green House Gas | 000000000634 | Substances | REAL_SUB
Heat Transfer Fluid | 000000000324 | Substances | REAL_SUB
Heavy Fuel Oil | 000000000325 | Substances | REAL_SUB
Heptafluoropropane | 000000000660 | Substances | REAL_SUB
Heptane | 000000000326 | Substances | REAL_SUB
Herbicide | 000000000327 | Substances | REAL_SUB
Hexanes | 000000000328 | Substances | REAL_SUB
Hydrocarbons | 000000000329 | Substances | REAL_SUB
Hydrochloric Acid | 000000000330 | Substances | REAL_SUB
Hydrofluoric Acid | 000000000331 | Substances | REAL_SUB
Hydrogen | 000000000332 | Substances | REAL_SUB
Hydrogen Cyanide | 000000000635 | Substances | REAL_SUB
Hydrogen Fluoride | 000000000636 | Substances | REAL_SUB
Hydrogen Sulfide | 000000000637 | Substances | REAL_SUB
Insecticide | 000000000594 | Substances | REAL_SUB
Iron Chlorate | 000000000333 | Substances | REAL_SUB
Iron Oxide | 000000000334 | Substances | REAL_SUB
Iso-cyanates | 000000000335 | Substances | REAL_SUB
Iso-propyl Alcohol | 000000000336 | Substances | REAL_SUB
Kaolin | 000000000337 | Substances | REAL_SUB
Kerosene | 000000000338 | Substances | REAL_SUB
Lead | 000000000339 | Substances | REAL_SUB
Lead Carbonate | 000000000492 | Substances | REAL_SUB
Liquid Petroleum Gas (Propane) | 000000000341 | Substances | REAL_SUB
Lubricant | 000000000342 | Substances | REAL_SUB
Manganese | 000000000654 | Substances | REAL_SUB
Mercury | 000000000343 | Substances | REAL_SUB
Metal Leachate (ARD) | 000000000721 | Substances | REAL_SUB
Metallic Fumes | 000000000638 | Substances | REAL_SUB
Methane | 000000000344 | Substances | REAL_SUB
Methyl Cyclopentane | 000000000345 | Substances | REAL_SUB
Methyl Ethyl Ketone | 000000000346 | Substances | REAL_SUB
Methyl Isobutyl Carbinol (MIBC) | 000000000347 | Substances | REAL_SUB
Methyl Isobutyl Ketone | 000000000348 | Substances | REAL_SUB
Methylated Spirits (Denatured Alcohol) | 000000000543 | Substances | REAL_SUB
Mica | 000000000583 | Substances | REAL_SUB
Molybdenum | 000000000655 | Substances | REAL_SUB
Natural Gas | 000000000349 | Substances | REAL_SUB
N-Butanol | 000000000350 | Substances | REAL_SUB
N-Hexane | 000000000351 | Substances | REAL_SUB
Nickel | 000000000352 | Substances | REAL_SUB
Nitric Acid | 000000000353 | Substances | REAL_SUB
Nitrogen | 000000000354 | Substances | REAL_SUB
Nitrogen - Liquid Cryogenic | 000000000496 | Substances | REAL_SUB
Nitrogen Dioxide | 000000000639 | Substances | REAL_SUB
Nitroglycerine | 000000000497 | Substances | REAL_SUB
Nitrous Oxide | 000000000640 | Substances | REAL_SUB
Non Asbestos Fibrous Silicates (NAFS) | 000000000641 | Substances | REAL_SUB
Nonane | 000000000357 | Substances | REAL_SUB
N-Pentane | 000000000358 | Substances | REAL_SUB
Octane | 000000000359 | Substances | REAL_SUB
Oil Mist | 000000000360 | Substances | REAL_SUB
Oils | 000000000361 | Substances | REAL_SUB
Organic Peroxides | 000000000362 | Substances | REAL_SUB
Organic Vapours | 000000000642 | Substances | REAL_SUB
Oxygen | 000000000364 | Substances | REAL_SUB
Oxygen - Liquid Crygenic | 000000000499 | Substances | REAL_SUB
Ozone | 000000000365 | Substances | REAL_SUB
Paint | 000000000366 | Substances | REAL_SUB
Paint Thinners | 000000000595 | Substances | REAL_SUB
Paraffins -Liquid | 000000000596 | Substances | REAL_SUB
Per Fluorocarbons | 000000000367 | Substances | REAL_SUB
Pesticide | 000000000598 | Substances | REAL_SUB
Petrol (Gasoline) | 000000000656 | Substances | REAL_SUB
Phosgene | 000000000369 | Substances | REAL_SUB
Phosphate | 000000000370 | Substances | REAL_SUB
Phosphoric Acid | 000000000500 | Substances | REAL_SUB
Plastic | 000000000371 | Substances | REAL_SUB
Poly Aromatic Hydrocarbons | 000000000372 | Substances | REAL_SUB
Polychlorinated Biphenyls | 000000000373 | Substances | REAL_SUB
Polychlorinated Dioxins | 000000000374 | Substances | REAL_SUB
Polychlorinated Furans | 000000000375 | Substances | REAL_SUB
Potassium | 000000000376 | Substances | REAL_SUB
Potassium Chloride | 000000000377 | Substances | REAL_SUB
Potassium Hydrogen Silica | 000000000378 | Substances | REAL_SUB
Process Slurry | 000000000379 | Substances | REAL_SUB
Process Water | 000000000380 | Substances | REAL_SUB
Propane | 000000000381 | Substances | REAL_SUB
Refrigerant Gas | 000000000643 | Substances | REAL_SUB
Reproductive Toxicants | 000000000384 | Substances | REAL_SUB
Respirable Crystalline Silica | 000000000644 | Substances | REAL_SUB
Rubber | 000000000385 | Substances | REAL_SUB
Saline Water | 000000000386 | Substances | REAL_SUB
Selenium | 000000000645 | Substances | REAL_SUB
Sewage Effluent | 000000000387 | Substances | REAL_SUB
Silver | 000000000390 | Substances | REAL_SUB
Silver Nitrate | 000000000391 | Substances | REAL_SUB
Sodium | 000000000392 | Substances | REAL_SUB
Sodium Bifluoride | 000000000657 | Substances | REAL_SUB
Sodium Carbonate | 000000000394 | Substances | REAL_SUB
Sodium Chloride | 000000000395 | Substances | REAL_SUB
Sodium Cyanide | 000000000396 | Substances | REAL_SUB
Sodium Ferrocyanide | 000000000658 | Substances | REAL_SUB
Sodium Fluoride | 000000000397 | Substances | REAL_SUB
Sodium Gluconate | 000000000398 | Substances | REAL_SUB
Sodium Hydrosulfide | 000000000734 | Substances | REAL_SUB
Sodium Hydrosulfite | 000000000502 | Substances | REAL_SUB
Sodium Hydroxide | 000000000399 | Substances | REAL_SUB
Sodium Hypochlorite | 000000000400 | Substances | REAL_SUB
Sodium Metabisulfate | 000000000587 | Substances | REAL_SUB
Sodium Oxalate | 000000000401 | Substances | REAL_SUB
Sodium Sulfate | 000000000402 | Substances | REAL_SUB
Sodium Sulfide | 000000000505 | Substances | REAL_SUB
Sodium Tetraborate | 000000000403 | Substances | REAL_SUB
Sodium Thiosulfate | 000000000506 | Substances | REAL_SUB
Soil (contaminated) | 000000000584 | Substances | REAL_SUB
Solvents | 000000000404 | Substances | REAL_SUB
Spent Cell Lining or Spent Pot Lining | 000000000406 | Substances | REAL_SUB
Sulfur | 000000000585 | Substances | REAL_SUB
Sulfur Dioxide | 000000000647 | Substances | REAL_SUB
Sulfur Trioxide | 000000000650 | Substances | REAL_SUB
Sulfuric Acid | 000000000408 | Substances | REAL_SUB
Sulfuric Acid Mist | 000000000646 | Substances | REAL_SUB
Sulphur Hexafluoride | 000000000407 | Substances | REAL_SUB
Suspended Solids | 000000000727 | Substances | REAL_SUB
Talc | 000000000611 | Substances | REAL_SUB
Tar | 000000000409 | Substances | REAL_SUB
Thallium | 000000000410 | Substances | REAL_SUB
Thiourea | 000000000510 | Substances | REAL_SUB
Titanium Dioxide Slag | 000000000733 | Substances | REAL_SUB
Toluene | 000000000412 | Substances | REAL_SUB
Tributyl Tin | 000000000415 | Substances | REAL_SUB
Trichloroethylene | 000000000511 | Substances | REAL_SUB
Trichloroisocyanuric Acid | 000000000597 | Substances | REAL_SUB
Uranium | 000000000417 | Substances | REAL_SUB
Vanadium | 000000000418 | Substances | REAL_SUB
Volatile Organic Carbons | 000000000648 | Substances | REAL_SUB
Welding Fumes | 000000000649 | Substances | REAL_SUB
Xylene | 000000000420 | Substances | REAL_SUB
Zinc | 000000000612 | Substances | REAL_SUB
Algae | 000000000001 | Biological | ZBIOLOG
Avian Flu | 000000000003 | Biological | ZBIOLOG
Bacteria | 000000000004 | Biological | ZBIOLOG
Blood Products | 000000000005 | Biological | ZBIOLOG
Bodily Fluid | 000000000006 | Biological | ZBIOLOG
Faecal Biota | 000000000009 | Biological | ZBIOLOG
Flora | 000000000011 | Biological | ZBIOLOG
Flora Weed | 000000000012 | Biological | ZBIOLOG
Fungi | 000000000014 | Biological | ZBIOLOG
HIV/AIDS | 000000000017 | Biological | ZBIOLOG
Insects / spiders | 000000000018 | Biological | ZBIOLOG
Legionella | 000000000020 | Biological | ZBIOLOG
Livestock | 000000000032 | Biological | ZBIOLOG
Marine Life | 000000000022 | Biological | ZBIOLOG
Micro-organisms - non-specific | 000000000574 | Biological | ZBIOLOG
Parasites | 000000000023 | Biological | ZBIOLOG
Rodents | 000000000026 | Biological | ZBIOLOG
Sharps | 000000000030 | Biological | ZBIOLOG
Viruses | 000000000034 | Biological | ZBIOLOG
Wildlife | 000000000036 | Biological | ZBIOLOG
Avalanche | 000000000517 | Climatic / Natural Events | ZCLIMATIC
Blizzard | 000000000037 | Climatic / Natural Events | ZCLIMATIC
Cyclones / Hurricanes / Typhoons | 000000000039 | Climatic / Natural Events | ZCLIMATIC
Drought | 000000000040 | Climatic / Natural Events | ZCLIMATIC
Earthquake | 000000000041 | Climatic / Natural Events | ZCLIMATIC
Fire - Bushfire/Wildfire/Grassfire | 000000000038 | Climatic / Natural Events | ZCLIMATIC
Flood | 000000000042 | Climatic / Natural Events | ZCLIMATIC
Foggy / Misty Conditions | 000000000575 | Climatic / Natural Events | ZCLIMATIC
Hail | 000000000581 | Climatic / Natural Events | ZCLIMATIC
Ice | 000000000044 | Climatic / Natural Events | ZCLIMATIC
Landslides | 000000000045 | Climatic / Natural Events | ZCLIMATIC
Lightning | 000000000046 | Climatic / Natural Events | ZCLIMATIC
Muddy Conditions | 000000000576 | Climatic / Natural Events | ZCLIMATIC
Rain | 000000000542 | Climatic / Natural Events | ZCLIMATIC
Snow | 000000000047 | Climatic / Natural Events | ZCLIMATIC
Storms | 000000000048 | Climatic / Natural Events | ZCLIMATIC
Tornado | 000000000515 | Climatic / Natural Events | ZCLIMATIC
Tsunami | 000000000049 | Climatic / Natural Events | ZCLIMATIC
Volcanic Eruption | 000000000571 | Climatic / Natural Events | ZCLIMATIC
Volcanic event | 000000000739 | Climatic / Natural Events | ZCLIMATIC
Wind | 000000000516 | Climatic / Natural Events | ZCLIMATIC
Aircraft | 000000000067 | Vehicles/transportation | ZCOLLISION
Ancillary Equipment | 000000000064 | Vehicles/transportation | ZCOLLISION
Bicycle / cyclist | 000000000055 | Vehicles/transportation | ZCOLLISION
Cranes | 000000000059 | Vehicles/transportation | ZCOLLISION
Draglines | 000000000062 | Vehicles/transportation | ZCOLLISION
Earthmoving equipment | 000000000060 | Vehicles/transportation | ZCOLLISION
Hazardous material transport | 000000000738 | Vehicles/transportation | ZCOLLISION
Heavy Vehicles | 000000000052 | Vehicles/transportation | ZCOLLISION
Light/Medium Vehicles | 000000000053 | Vehicles/transportation | ZCOLLISION
Marine Vessels / Ships | 000000000057 | Vehicles/transportation | ZCOLLISION
Mining Equipment | 000000000061 | Vehicles/transportation | ZCOLLISION
Molten metal transport | 000000000065 | Vehicles/transportation | ZCOLLISION
Motorcycles | 000000000054 | Vehicles/transportation | ZCOLLISION
Remote controlled equipment | 000000000066 | Vehicles/transportation | ZCOLLISION
Small Boat / Watercraft | 000000000599 | Vehicles/transportation | ZCOLLISION
Stackers / reclaimers | 000000000063 | Vehicles/transportation | ZCOLLISION
Trains | 000000000068 | Vehicles/transportation | ZCOLLISION
AC <110 Volts | 000000000520 | Electrical / Magnetic | ZELECTRIC
AC 110-480 Volts | 000000000522 | Electrical / Magnetic | ZELECTRIC
AC 240 Volts | 000000000070 | Electrical / Magnetic | ZELECTRIC
AC 50 Volts | 000000000069 | Electrical / Magnetic | ZELECTRIC
Arc Flash | 000000000737 | Electrical / Magnetic | ZELECTRIC
Control Systems | 000000000073 | Electrical / Magnetic | ZELECTRIC
DC <24 Volts | 000000000523 | Electrical / Magnetic | ZELECTRIC
DC 110 Volts | 000000000071 | Electrical / Magnetic | ZELECTRIC
DC 240 Volts | 000000000072 | Electrical / Magnetic | ZELECTRIC
DC Earth Leakage | 000000000074 | Electrical / Magnetic | ZELECTRIC
DC Open Circuit | 000000000075 | Electrical / Magnetic | ZELECTRIC
DC Short Circuit | 000000000076 | Electrical / Magnetic | ZELECTRIC
High Voltage (>480 Volts) | 000000000077 | Electrical / Magnetic | ZELECTRIC
Induced current | 000000000736 | Electrical / Magnetic | ZELECTRIC
Loss of Power | 000000000078 | Electrical / Magnetic | ZELECTRIC
Low Voltage | 000000000079 | Electrical / Magnetic | ZELECTRIC
Magnetic Fields - Geomagnetic | 000000000080 | Electrical / Magnetic | ZELECTRIC
Magnetic Fields Intensity | 000000000081 | Electrical / Magnetic | ZELECTRIC
Static Electricity | 000000000083 | Electrical / Magnetic | ZELECTRIC
Dredging | 000000000153 | Natural environment/ecosystem | ZENVIRON
Ecosystem Change | 000000000154 | Natural environment/ecosystem | ZENVIRON
Electrical energy consumption | 000000000766 | Natural environment/ecosystem | ZENVIRON
Erosion | 000000000711 | Natural environment/ecosystem | ZENVIRON
Fuel consumption | 000000000767 | Natural environment/ecosystem | ZENVIRON
Land Filling | 000000000155 | Natural environment/ecosystem | ZENVIRON
Topography Modification | 000000000157 | Natural environment/ecosystem | ZENVIRON
Vegetation Clearing | 000000000158 | Natural environment/ecosystem | ZENVIRON
Water Abstraction | 000000000580 | Natural environment/ecosystem | ZENVIRON
Waterway Diversion | 000000000160 | Natural environment/ecosystem | ZENVIRON
Bending/Twisting | 000000000577 | Ergonomics | ZERGONOMIC
Hand Tool Use | 000000000162 | Ergonomics | ZERGONOMIC
Load Handling | 000000000163 | Ergonomics | ZERGONOMIC
Pushing and Pulling | 000000000165 | Ergonomics | ZERGONOMIC
Repetitive Motion Actions | 000000000166 | Ergonomics | ZERGONOMIC
Vibration - Hand/Arm | 000000000602 | Ergonomics | ZERGONOMIC
Vibration - Whole Body | 000000000525 | Ergonomics | ZERGONOMIC
Work Area Design | 000000000550 | Ergonomics | ZERGONOMIC
Bench Stability | 000000000176 | Gravity | ZGRAVITY
Dump Stability | 000000000177 | Gravity | ZGRAVITY
Fall at Level | 000000000178 | Gravity | ZGRAVITY
Fall from Height | 000000000183 | Gravity | ZGRAVITY
Fall into Depths | 000000000184 | Gravity | ZGRAVITY
Falling Load | 000000000181 | Gravity | ZGRAVITY
Falling Object / Material | 000000000179 | Gravity | ZGRAVITY
High Wall / Low Walls Stability | 000000000185 | Gravity | ZGRAVITY
Roll Away | 000000000186 | Gravity | ZGRAVITY
Roll Over | 000000000579 | Gravity | ZGRAVITY
Slope Stability | 000000000187 | Gravity | ZGRAVITY
Underground strata stability | 000000000191 | Gravity | ZGRAVITY
Glare | 000000000192 | Lighting | ZLIGHT
High Level | 000000000193 | Lighting | ZLIGHT
Low Level | 000000000194 | Lighting | ZLIGHT
Crushing | 000000000198 | Mechanical | ZMECHANIC
Cutting or Severing | 000000000199 | Mechanical | ZMECHANIC
Grinding | 000000000204 | Mechanical | ZMECHANIC
Impact | 000000000205 | Mechanical | ZMECHANIC
Mass and Stability | 000000000206 | Mechanical | ZMECHANIC
Mass and Velocity | 000000000207 | Mechanical | ZMECHANIC
Mechanical Strength | 000000000208 | Mechanical | ZMECHANIC
Moving Equipment | 000000000552 | Mechanical | ZMECHANIC
Pinch Points | 000000000209 | Mechanical | ZMECHANIC
Projectile | 000000000603 | Mechanical | ZMECHANIC
Puncturing | 000000000210 | Mechanical | ZMECHANIC
Roll-Over | 000000000211 | Mechanical | ZMECHANIC
Rotating Equipment | 000000000578 | Mechanical | ZMECHANIC
Stored Energy | 000000000201 | Mechanical | ZMECHANIC
Vacuum | 000000000212 | Mechanical | ZMECHANIC
Wearing / Scraping | 000000000197 | Mechanical | ZMECHANIC
Abnormal Long Work Hours | 000000000213 | Personal / Behavioural | ZPERBEHA
Aggressive Behaviour | 000000000214 | Personal / Behavioural | ZPERBEHA
Alcohol / Drug Abuse | 000000000215 | Personal / Behavioural | ZPERBEHA
Fatigue | 000000000218 | Personal / Behavioural | ZPERBEHA
Harassment | 000000000219 | Personal / Behavioural | ZPERBEHA
Non-adherence to policies/procedures | 000000000553 | Personal / Behavioural | ZPERBEHA
Reduced capacity for work - mental | 000000000752 | Personal / Behavioural | ZPERBEHA
Reduced capacity for work - physical | 000000000751 | Personal / Behavioural | ZPERBEHA
Shift Work | 000000000226 | Personal / Behavioural | ZPERBEHA
Stress | 000000000220 | Personal / Behavioural | ZPERBEHA
Violence / Crime | 000000000231 | Personal / Behavioural | ZPERBEHA
Air (eg. Tyres) | 000000000239 | Pressure | ZPRESSURE
Artesian | 000000000232 | Pressure | ZPRESSURE
Ground | 000000000233 | Pressure | ZPRESSURE
Hydraulic | 000000000234 | Pressure | ZPRESSURE
Hydrostatic | 000000000235 | Pressure | ZPRESSURE
Inrush | 000000000236 | Pressure | ZPRESSURE
Mechanical | 000000000237 | Pressure | ZPRESSURE
Pneumatic | 000000000238 | Pressure | ZPRESSURE
Steam | 000000000604 | Pressure | ZPRESSURE
Wind Blast | 000000000240 | Pressure | ZPRESSURE
Electromagnetic Radiation | 000000000241 | Radiation | ZRADIAT
Gamma / X-rays | 000000000691 | Radiation | ZRADIAT
Infrared | 000000000242 | Radiation | ZRADIAT
Laser | 000000000245 | Radiation | ZRADIAT
Radioactive Dusts | 000000000248 | Radiation | ZRADIAT
Radioactive Gauges | 000000000247 | Radiation | ZRADIAT
Radiofrequency & Microwave | 000000000249 | Radiation | ZRADIAT
Radon, Thoron and Decay Products | 000000000250 | Radiation | ZRADIAT
Ultraviolet | 000000000251 | Radiation | ZRADIAT
Welding Flash | 000000000252 | Radiation | ZRADIAT
X Ray Apparatus | 000000000253 | Radiation | ZRADIAT
Noise (Community Issue) | 000000000730 | Sound / Vibration | ZSND_VIB
Noise (Continuous) | 000000000256 | Sound / Vibration | ZSND_VIB
Noise (Impact) | 000000000257 | Sound / Vibration | ZSND_VIB
Vibration (Community issue) | 000000000259 | Sound / Vibration | ZSND_VIB
Changes in Legal Systems | 000000000266 | Social / Cultural | ZSOCCULT
Cultural Heritage - Culture | 000000000706 | Social / Cultural | ZSOCCULT
Cultural Heritage - Sites | 000000000261 | Social / Cultural | ZSOCCULT
Discrimination | 000000000262 | Social / Cultural | ZSOCCULT
Economic / Community & Social Governance Capital | 000000000709 | Social / Cultural | ZSOCCULT
Economic / Community Rights | 000000000710 | Social / Cultural | ZSOCCULT
Economic / Human Capital | 000000000707 | Social / Cultural | ZSOCCULT
Economic / Livelihood - Financial Capital & Productive Activities | 000000000263 | Social / Cultural | ZSOCCULT
Economic / Natural Capital | 000000000708 | Social / Cultural | ZSOCCULT
Employment | 000000000264 | Social / Cultural | ZSOCCULT
Land & Infrastructure - Access | 000000000728 | Social / Cultural | ZSOCCULT
Land & Infrastructure - Acquisition | 000000000729 | Social / Cultural | ZSOCCULT
Relationships - Community Groups | 000000000723 | Social / Cultural | ZSOCCULT
Relationships - Government | 000000000724 | Social / Cultural | ZSOCCULT
Relationships - Media | 000000000726 | Social / Cultural | ZSOCCULT
Relationships - Non-government Organisations (NGOs) | 000000000725 | Social / Cultural | ZSOCCULT
Stakeholder Expectations | 000000000267 | Social / Cultural | ZSOCCULT
Subsistence and resource utlization | 000000000573 | Social / Cultural | ZSOCCULT
Ambient Heat | 000000000422 | Thermal/Fire/Explosion | ZTHERMAL
Cold Stress | 000000000423 | Thermal/Fire/Explosion | ZTHERMAL
Contact - Cold Gas | 000000000424 | Thermal/Fire/Explosion | ZTHERMAL
Contact - Cold Liquid | 000000000425 | Thermal/Fire/Explosion | ZTHERMAL
Contact - Cold Surface | 000000000426 | Thermal/Fire/Explosion | ZTHERMAL
Contact - Hot Gas | 000000000427 | Thermal/Fire/Explosion | ZTHERMAL
Contact - Hot Liquid | 000000000428 | Thermal/Fire/Explosion | ZTHERMAL
Contact - Hot Surface | 000000000429 | Thermal/Fire/Explosion | ZTHERMAL
Explosion - Dust | 000000000430 | Thermal/Fire/Explosion | ZTHERMAL
Explosion - Gas | 000000000432 | Thermal/Fire/Explosion | ZTHERMAL
Explosion - Mine | 000000000433 | Thermal/Fire/Explosion | ZTHERMAL
Explosion - Molten Material | 000000000434 | Thermal/Fire/Explosion | ZTHERMAL
Explosion - Underground | 000000000435 | Thermal/Fire/Explosion | ZTHERMAL
Extreme Cold | 000000000436 | Thermal/Fire/Explosion | ZTHERMAL
Extreme Heat | 000000000437 | Thermal/Fire/Explosion | ZTHERMAL
Fire - Surface - Fixed Plant | 000000000438 | Thermal/Fire/Explosion | ZTHERMAL
Fire - Surface - Mobile Plant | 000000000439 | Thermal/Fire/Explosion | ZTHERMAL
Fire - Underground - Fixed Plant | 000000000440 | Thermal/Fire/Explosion | ZTHERMAL
Fire - Underground - Mobile Plant | 000000000441 | Thermal/Fire/Explosion | ZTHERMAL
Heat Stress | 000000000442 | Thermal/Fire/Explosion | ZTHERMAL
Microwave | 000000000444 | Thermal/Fire/Explosion | ZTHERMAL
Molten Materials | 000000000445 | Thermal/Fire/Explosion | ZTHERMAL
Radiant Heat | 000000000446 | Thermal/Fire/Explosion | ZTHERMAL
Spontaneous Combustion | 000000000447 | Thermal/Fire/Explosion | ZTHERMAL
Arson | 000000000168 | External Threats | ZTHREAT
Bomb | 000000000169 | External Threats | ZTHREAT
Civil Unrest | 000000000170 | External Threats | ZTHREAT
Landmines | 000000000172 | External Threats | ZTHREAT
Political Unrest | 000000000171 | External Threats | ZTHREAT
Sabotage | 000000000174 | External Threats | ZTHREAT
Unauthorised Entry onto Site | 000000000175 | External Threats | ZTHREAT
War | 000000000173 | External Threats | ZTHREAT
Acid Generating Material | 000000000610 | Waste | ZWASTE
Base Generating Material | 000000000609 | Waste | ZWASTE
Biological | 000000000450 | Waste | ZWASTE
Clean Fill | 000000000451 | Waste | ZWASTE
Garden Waste | 000000000452 | Waste | ZWASTE
Hazardous Waste | 000000000454 | Waste | ZWASTE
Non Hazardous Waste | 000000000456 | Waste | ZWASTE
Non Specific | 000000000457 | Waste | ZWASTE
Office / Paper / Cardboard | 000000000460 | Waste | ZWASTE
Oil | 000000000459 | Waste | ZWASTE
Putrescible Materials | 000000000461 | Waste | ZWASTE
Radioactive Waste Materials | 000000000731 | Waste | ZWASTE
Scrap Metal | 000000000462 | Waste | ZWASTE
Tailings | 000000000463 | Waste | ZWASTE
Tyres | 000000000465 | Waste | ZWASTE
Water | 000000000466 | Waste | ZWASTE
Wood | 000000000467 | Waste | ZWASTE
Confined Spaces | 000000000468 | Work Environment | ZWORKENV
Dry Conditions | 000000000469 | Work Environment | ZWORKENV
Fixed Object | 000000000606 | Work Environment | ZWORKENV
Housekeeping | 000000000605 | Work Environment | ZWORKENV
Inadequate System Design | 000000000554 | Work Environment | ZWORKENV
Pedestrians | 000000000600 | Work Environment | ZWORKENV
Remote Activities / Isolation | 000000000471 | Work Environment | ZWORKENV
Travel Health | 000000000473 | Work Environment | ZWORKENV
Uneven or Broken Ground | 000000000582 | Work Environment | ZWORKENV
Ventilation | 000000000474 | Work Environment | ZWORKENV
Wet / Slick / Slippery Conditions | 000000000475 | Work Environment | ZWORKENV

## Operational_Status (hidden)
Operational Status Description | ABS Ref
Cleaning | R02
Closure | R10
Commissioning & Ramp Up | R09
Construction/Execution | R08
Decommissioning | R06
Disposal | R13
Emergency Conditions | R07
Energised Work (live testing) | R05
Exploration/Conceptual | R15
Feasibility | R16
In Transit | R12
Normal Operation | 000
Order of magnitude | R17
Planned Maintenance | R03
Post Closure/Care&Maintenance | R11
Prefeasibility | R18
Start Up/Pre Use | R14
Unplanned Maintenance | R04

## Category (hidden)
Category | ABS Ref
Capital expenditure | RT-020_000090
Community impact | RT-020_000170
Compliance impact | RT-020_000180
Environmental impact | RT-020_000160
Health impact | RT-020_000150
Operating cost | RT-020_000110
Personnel safety | RT-020_000140
Production volumes | RT-020_000120
Revenue | RT-020_000130
Rio Tinto or Business Unit Reputation | RT-020_000190
Schedule | RT-020_000100

## Sub_Category (hidden)
Sub Category | ABS Ref | Category | Category ABS Code
Inventory | RT-020_001230 | Capital expenditure | RT-020_000090
Unplanned/Forecast | RT-020_001240 | Capital expenditure | RT-020_000090
Change / Disruptions | RT-020_000800 | Schedule | RT-020_000100
Demurrage / Delays | RT-020_000810 | Schedule | RT-020_000100
Depreciation & Amortisation | RT-020_001810 | Operating cost | RT-020_000110
Employee Related costs | RT-020_001750 | Operating cost | RT-020_000110
Equipment/Property damage | RT-020_001690 | Operating cost | RT-020_000110
External Services | RT-020_001740 | Operating cost | RT-020_000110
General & Admin costs | RT-020_001770 | Operating cost | RT-020_000110
General Consumables (inc maintenance) | RT-020_001720 | Operating cost | RT-020_000110
Impairment | RT-020_001820 | Operating cost | RT-020_000110
Inventory Gains & Losses | RT-020_001790 | Operating cost | RT-020_000110
Inventory Price Variances | RT-020_001800 | Operating cost | RT-020_000110
Miscellaneous Expenses | RT-020_001840 | Operating cost | RT-020_000110
Non Operating Expenses | RT-020_001780 | Operating cost | RT-020_000110
Operating Supplies | RT-020_001710 | Operating cost | RT-020_000110
Raw Materials | RT-020_001700 | Operating cost | RT-020_000110
Royalties | RT-020_001760 | Operating cost | RT-020_000110
Special Purpose Accounts | RT-020_001830 | Operating cost | RT-020_000110
Utilities | RT-020_001730 | Operating cost | RT-020_000110
Inventory / Stockpile | RT-020_000660 | Production volumes | RT-020_000120
Quality - Contamination | RT-020_000670 | Production volumes | RT-020_000120
Quality - Out of specification | RT-020_000700 | Production volumes | RT-020_000120
Quantity / output | RT-020_000720 | Production volumes | RT-020_000120
Decrease | RT-020_000730 | Revenue | RT-020_000130
Increase | RT-020_000740 | Revenue | RT-020_000130
Abrasions | RT-020_000200 | Personnel safety | RT-020_000140
Acute Poisoning and Toxic Effects | RT-020_000520 | Personnel safety | RT-020_000140
Amputation | RT-020_000530 | Personnel safety | RT-020_000140
Asphyxiation | RT-020_000260 | Personnel safety | RT-020_000140
Blindness | RT-020_000540 | Personnel safety | RT-020_000140
Burns | RT-020_000280 | Personnel safety | RT-020_000140
Cardiac arrest | RT-020_000290 | Personnel safety | RT-020_000140
Crushing / internal injuries | RT-020_000300 | Personnel safety | RT-020_000140
Drowning | RT-020_000550 | Personnel safety | RT-020_000140
Electric shock | RT-020_000310 | Personnel safety | RT-020_000140
Electrocution | RT-020_000560 | Personnel safety | RT-020_000140
Engulfment | RT-020_000320 | Personnel safety | RT-020_000140
Entrapment | RT-020_000610 | Personnel safety | RT-020_000140
Inhalation (acute) | RT-020_000330 | Personnel safety | RT-020_000140
Injections / needle stick | RT-020_000340 | Personnel safety | RT-020_000140
Penetrations / open wounds | RT-020_000350 | Personnel safety | RT-020_000140
Pinching / Caught in or between | RT-020_000360 | Personnel safety | RT-020_000140
Security - Assault | RT-020_000630 | Personnel safety | RT-020_000140
Security - Civil/Community Unrest | RT-020_000640 | Personnel safety | RT-020_000140
Security - Unlawful access | RT-020_000650 | Personnel safety | RT-020_000140
Sprains / strains | RT-020_000370 | Personnel safety | RT-020_000140
Sudden Deafness/Hearing Loss | RT-020_000410 | Personnel safety | RT-020_000140
Cancers and Other Neoplasms | RT-020_001640 | Health impact | RT-020_000150
Cardiovascular System | RT-020_000390 | Health impact | RT-020_000150
Chronic Poisoning and Toxic Effects of Substances | RT-020_000420 | Health impact | RT-020_000150
Digestive System | RT-020_000440 | Health impact | RT-020_000150
Illness due to Physical Agents | RT-020_000400 | Health impact | RT-020_000150
Infectious and Parasitic | RT-020_000470 | Health impact | RT-020_000150
Mental Disorders | RT-020_001650 | Health impact | RT-020_000150
Nervous System and Sense Organs | RT-020_001660 | Health impact | RT-020_000150
Noise induced hearing loss (chronic exposure) | RT-020_001630 | Health impact | RT-020_000150
Repeated Trauma | RT-020_000500 | Health impact | RT-020_000150
Reproductive System | RT-020_001670 | Health impact | RT-020_000150
Respiratory System | RT-020_000460 | Health impact | RT-020_000150
Skin/Subcutaneous Tissue | RT-020_000380 | Health impact | RT-020_000150
Urinary System | RT-020_001680 | Health impact | RT-020_000150
Acid Rock Drainage (ARD) | RT-020_001480 | Environmental impact | RT-020_000160
Change to Visual Amenity | RT-020_000820 | Environmental impact | RT-020_000160
Consumption of Natural Resources | RT-020_002480 | Environmental impact | RT-020_000160
Contamination - Air | RT-020_001620 | Environmental impact | RT-020_000160
Contamination - Other | RT-020_001490 | Environmental impact | RT-020_000160
Contamination - Radioactive | RT-020_001500 | Environmental impact | RT-020_000160
Contamination - Soil | RT-020_001510 | Environmental impact | RT-020_000160
Contamination - Toxics | RT-020_001520 | Environmental impact | RT-020_000160
Contamination - Water | RT-020_001530 | Environmental impact | RT-020_000160
Eutrophication | RT-020_001540 | Environmental impact | RT-020_000160
Habitat Disturbance | RT-020_000600 | Environmental impact | RT-020_000160
Habitat Loss | RT-020_001550 | Environmental impact | RT-020_000160
Interactions with Air | RT-020_000590 | Environmental impact | RT-020_000160
Interactions with estuarine/marine | RT-020_000620 | Environmental impact | RT-020_000160
Interactions with Fauna (general) | RT-020_000570 | Environmental impact | RT-020_000160
Interactions with Flora (general) | RT-020_000580 | Environmental impact | RT-020_000160
Interactions with Groundwater | RT-020_001560 | Environmental impact | RT-020_000160
Interactions with rare and endangered Fauna | RT-020_001570 | Environmental impact | RT-020_000160
Interactions with rare and endangered Flora | RT-020_001580 | Environmental impact | RT-020_000160
Interactions with Surfacewater | RT-020_000710 | Environmental impact | RT-020_000160
Non-native species | RT-020_001600 | Environmental impact | RT-020_000160
Nuisance Odour | RT-020_000690 | Environmental impact | RT-020_000160
Nutrient Loading | RT-020_001610 | Environmental impact | RT-020_000160
Pest infestation | RT-020_000680 | Environmental impact | RT-020_000160
Access | RT-020_001250 | Community impact | RT-020_000170
Community Trust | RT-020_002470 | Community impact | RT-020_000170
Complaint | RT-020_001260 | Community impact | RT-020_000170
Cultural Heritage | RT-020_000830 | Community impact | RT-020_000170
Demonstrations/ Protests | RT-020_000840 | Community impact | RT-020_000170
Media | RT-020_000850 | Community impact | RT-020_000170
Socio-economic effects | RT-020_000270 | Community impact | RT-020_000170
Stakeholders | RT-020_000860 | Community impact | RT-020_000170
Commitment - formal | RT-020_001430 | Compliance impact | RT-020_000180
Commitment - informal | RT-020_001440 | Compliance impact | RT-020_000180
Commitment/Contract | RT-020_001270 | Compliance impact | RT-020_000180
Contract / service agreement | RT-020_001280 | Compliance impact | RT-020_000180
Court order (potential) | RT-020_001290 | Compliance impact | RT-020_000180
External permit | RT-020_001300 | Compliance impact | RT-020_000180
External standard | RT-020_001310 | Compliance impact | RT-020_000180
Legal Agreement | RT-020_001450 | Compliance impact | RT-020_000180
Legislation (potential) | RT-020_001320 | Compliance impact | RT-020_000180
License - external (potential) | RT-020_001330 | Compliance impact | RT-020_000180
Non-conformance: Internal work permit | RT-020_001340 | Compliance impact | RT-020_000180
Non-conformance: Objective / Target | RT-020_001350 | Compliance impact | RT-020_000180
Non-conformance: Policy | RT-020_001360 | Compliance impact | RT-020_000180
Non-conformance: Procedure / Work instruction | RT-020_001370 | Compliance impact | RT-020_000180
Non-conformance: Standard | RT-020_001380 | Compliance impact | RT-020_000180
Non-conformance: System certification | RT-020_001390 | Compliance impact | RT-020_000180
Non-conformance: Work cycle / work practice | RT-020_001400 | Compliance impact | RT-020_000180
Promise - formal | RT-020_001460 | Compliance impact | RT-020_000180
Promise - informal | RT-020_001470 | Compliance impact | RT-020_000180
Regulation (potential) | RT-020_001410 | Compliance impact | RT-020_000180
Voluntary subscription | RT-020_001420 | Compliance impact | RT-020_000180
Customer / Stakeholder Complaint | RT-020_000750 | Rio Tinto or Business Unit Reputation | RT-020_000190
Customer Service | RT-020_000770 | Rio Tinto or Business Unit Reputation | RT-020_000190
Negative | RT-020_000780 | Rio Tinto or Business Unit Reputation | RT-020_000190
Positive | RT-020_000790 | Rio Tinto or Business Unit Reputation | RT-020_000190

## Source (hidden)
Source | ABS Ref
B1 Particulates & Gas Vapour Exposure | B1
B10 Occupational Exposure Limits | B10
B11 HIV / AIDS | B11
B2 Hearing Conservation | B2
B3 Manual Handling & Vibration | B3
B4 Hazardous Substances | B4
B5 Radiation | B5
B6 Thermal Stress | B6
B7 Fitness for Work | B7
B8 Legionella | B8
B9 Travel and Remote Site Health | B9
C1 Isolation | C1
C2 Electrical Safety | C2
C3 Vehicles and Driving | C3
C4 Working At Heights | C4
C5 Confined Spaces | C5
C6 Cranes and Lifting Equipment | C6
C7 Aviation | C7
D1.1 Underground: Ground Control | D1.1
D1.2 Underground: Emergency Procedures | D1.2
D1.3 Underground: Fire Precautions | D1.3
D1.4 Underground: Hoisting | D1.4
D2 Molten Materials | D2
D3 Management of pit slopes, stockpiles, spoils and waste dumps
D4.1 Mooring Ops at Wharves & Ships
E10 Water Use & Quality Control | E10
E2 Air Quality Control | E2
E3 Acid Rock Drainage Prediction and Control | E3
E4 Greenhouse Gas Emissions | E4
E5 Hazardous Material and Contamination Control | E5
E6 Noise & Vibration Control | E6
E7 Non-Mineral Waste Management | E7
E8 Mineral Waste Management | E8
E9 Land-Use Stewardship | E9
Legal Compliance | COMPLIANCE
M1 Policy | M1
M10 Operational Control | M10
M11 Management of Change | M11
M12 Disaster Management & Recovery | M12
M13 Measuring & Monitoring | M13
M14 Non-conformance, Incident & Action Management | M14
M15 Data & Records Management & Action Management | M15
M16 Performance Assessment & Audit | M16
M17 Management Review | M17
M2 Legal & Other Requirements | M2
M3 Hazard ID & Risk Management | M3
M4 HSEQ Management Improvement Planning | M4
M5 Organisation Accountabilities & Responsibilities | M5
M6 Training Competency & Awareness | M6
M7 Contractor Management | M7
M8 Document Control | M8
M9 Communications & Consultation | M9

## Status (hidden)
Status Description | ABS Ref
1 In Process | I0439
2 For Review | I0440
3 Released | I0442

## Likelihood (hidden)
Likelihood | ABS Ref
A-Almost certain | A
B-Likely | B
C-Possible | C
D-Unlikely | D
E-Rare | E

## Consequence (hidden)
Consequence | ABS Ref
1-Minor | 1
2-Medium | 2
3-Serious | 3
4-Major | 4
5-Catastrophic | 5

## Cause (hidden)
Cause Description | ABS Ref
Communications | RT-020_001000
Communications-Misunderstood verbal communication | RT-020_001030
Communications-No communication or not timely | RT-020_001010
Communications-Turnover needs improvement | RT-020_001020
Equipment difficulty | RT-020_001180
Equipment difficulty-Design | RT-020_001900
Equipment difficulty-Equipment / parts defective | RT-020_001910
Equipment difficulty-Preventative / predictive maintenance | RT-020_001920
Equipment difficulty-Repeat failure | RT-020_001860
Equipment difficulty-Tolerable failure | RT-020_001890
Human engineering | RT-020_001090
Human engineering-Complex system | RT-020_001120
Human engineering-Human-machine interface | RT-020_001100
Human engineering-Non-fault tolerant system | RT-020_001130
Human engineering-Work environment | RT-020_001110
Human performance difficulty | RT-020_000890
Management system | RT-020_001040
Management system-Corrective action | RT-020_001080
Management system-Oversight/employee relations | RT-020_001070
Management system-Standards, policies or admin controls need improvement | RT-020_001050
Management system-Standards, policies or admin controls not used | RT-020_001060
Natural disaster / sabotage | RT-020_001870
Other (specify) | RT-020_001880
Procedures | RT-020_000900
Procedures-Followed Incorrectly | RT-020_000930
Procedures-Not used/not followed | RT-020_000910
Procedures-Wrong | RT-020_000920
Quality control | RT-020_000970
Quality control-No inspection | RT-020_000980
Quality control-Quality control needs improvement | RT-020_000990
Training | RT-020_000940
Training-No training | RT-020_000950
Training-Understanding needs improvement | RT-020_000960
Work direction | RT-020_001140
Work direction-Preparation | RT-020_001150
Work direction-Selection of worker | RT-020_001160
Work direction-Supervision during work | RT-020_001170

## Control_Type (hidden)
Control Type Description | ABS Ref
1 Elimination | 1
2 Substitution | 2
3 Engineering Controls | 3
4 Administrative Controls | 4
5 Personal Protective Equipment (PPE) | 5

## QA_Risk_Class (hidden)
Quantitative Risk Class | ABS Ref
I Low | RT-020_001930
II Moderate | RT-020_001940
III High | RT-020_001950
IV Critical | RT-020_001960